## Sheet1
Documentation
| Abstract |  | Charlotte
Research
|  | Market Research | Rich/Steve | Before freshers week
|  | Target Audience | Charlotte/Ben | Before freshers week
Scope
|  | Purpose | Ben | Before freshers week
|  | Objectives | Ben | Before freshers week
| Requirements |  | Stephen | Before freshers week
Schedule
|  | Gannt Chart | Charlotte | Before freshers week
|  | Network Diagram | Stephen | Before freshers week
|  | Use Cases | Rich | Before freshers week
Quality Management
|  | QA Doocument | Ben | Before freshers week
|  | Test Plan |  | Ongoing
Stakeholders
|  | StakeholdderPlan | Rich | Before freshers week
|  | Stakeholder Analysis | Rich | Before freshers week
Change Management
|  | Change Management Plan | Rich | Before freshers week
Risk Management
|  | Project Risk Assessment | Stephen | Before freshers week
|  | Feasibility Study | Stephen | Before freshers week
Justification
|  | Why android? | Charlotte | Before freshers week
|  | Why Agille? | Ben | Before freshers week
|  | Why WebApp/Android?? | Ben | Before freshers week
Iteration 1
Iteration Plan
Aims
Design
Design Test Cases
Database Design
Entity Relationship Diagram
Conceptual Data Model
Logical Data Model
Physical Data Model
Database Creation
Database Testing
Database Test Results
Create web login Screen
Test Login Screen
Iteration 2
Iteration Plan
Aims
Design
Design Test Cases
Create login screen for app
Implement home screen for carers and patients for web.
Implement home screen for carers and patients for app.
Testing
Testing Results

## Sheet2
Just Health Gannt Chart V2
Task Name |  | Start Date | Duration (days) | End Date | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 29/09/2014(Week 1) | 06/10/2014 (Week 2) | 13/10/2014 (Week 3) | 20/10/2014 (Week 4) | 27/10/2014 (Week 5) | 03/11/2014 (Week 6) | 10/11/2014 (Week 7) | 17/11/14 (Week 8) | 24/11/14 (Week 9)
Documentation and Planning |  | 2014-08-06 | 47 | 2014-09-22
Abstract
| Research | 2014-08-06 | 28 | 2014-09-03
| Market Research | 2014-08-06 | 28 | 2014-09-03
| Target Audience | 2014-08-06 | 28 | 2014-09-03
| Scope | 2014-08-04 | 49 | 2014-09-22
| Purpose | 2014-08-04 | 49 | 2014-09-22
| Objectives | 2014-08-04 | 49 | 2014-09-22
| Gather Requirements | 2014-08-06 | 47 | 2014-09-22
| Schedule | 2014-08-03 | 50 | 2014-09-22
| Gannt Chart | 2014-08-03 | 50 | 2014-09-22
| Network Diagram | 2014-08-03 | 50 | 2014-09-22
| Legal Documentation | 2014-08-03 | 50 | 2014-09-22
| Quality Management | 2014-08-03 | 50 | 2014-09-22
| QA Doocument | 2014-08-03 | 50 | 2014-09-22
| Test Plan | 2014-08-03 | 50 | 2014-09-22
| Stakeholders | 2014-08-03 | 50 | 2014-09-22
| StakeholdderPlan | 2014-08-03 | 50 | 2014-09-22
| Stakeholder Analysis | 2014-08-03 | 50 | 2014-09-22
| Change Management | 2014-08-03 | 50 | 2014-09-22
| Change Management Plan | 2014-08-03 | 50 | 2014-09-22
| Risk Management | 2014-08-03 | 50 | 2014-09-22
| Project Risk Assessment | 2014-08-03 | 50 | 2014-09-22
| Feasibility Study | 2014-08-03 | 50 | 2014-09-22
| Justification | 2014-08-03 | 50 | 2014-09-22
| Why android? | 2014-08-03 | 50 | 2014-09-22
| Why Agille? | 2014-08-03 | 50 | 2014-09-22
| Why WebApp/Android?? | 2014-08-03 | 50 | 2014-09-22
| Issue tracking template and documentation | 2014-09-22 | 7 | 2014-09-29
| Questionnaires | 2014-09-22 | 7 | 2014-09-29
Iteration 1 |  | 2014-09-22 | 14 | 2014-10-06
| Iteration Plan | 2014-09-22 | 14 | 2014-10-06
| Aims | 2014-09-22 | 14 | 2014-10-06
| Design | 2014-09-22 | 14 | 2014-10-06
| Test plan | 2014-09-22 | 14 | 2014-10-06
| Design Test Cases | 2014-09-22 | 14 | 2014-10-06
| Usecases | 2014-09-22 | 14 | 2014-10-06
Password Research
| Database Design | 2014-09-22 | 14 | 2014-10-06
| Entity Relationship Diagram | 2014-09-22 | 14 | 2014-10-06
| Conceptual Data Model | 2014-09-22 | 14 | 2014-10-06
| Logical Data Model | 2014-09-22 | 14 | 2014-10-06
| Physical Data Model | 2014-09-22 | 14 | 2014-10-06
| Database Creation | 2014-09-22 | 14 | 2014-10-06
| Database Testing | 2014-09-22 | 14 | 2014-10-06
| Database Test Results | 2014-09-22 | 14 | 2014-10-06
| Create Profile and Register | 2014-09-22 | 14 | 2014-10-06
| Create login Screen | 2014-09-22 | 14 | 2014-10-06
| Test Login Screen | 2014-09-22 | 14 | 2014-10-06
Iteration 2 |  | 2014-10-06 | 14 | 2014-10-20
| Iteration Plan | 2014-10-06 | 14 | 2014-10-20
| Aims | 2014-10-06 | 14 | 2014-10-20
| Design | 2014-10-06 | 14 | 2014-10-20
Test Plan
| Design Test Cases | 2014-10-06 | 14 | 2014-10-20
| Usecases | 2014-10-06 | 14 | 2014-10-20
Create Profile and Register
| Create login screen | 2014-10-06 | 14 | 2014-10-20
| Patient/Carer home screen | 2014-10-06 | 14 | 2014-10-20
| Testing | 2014-10-06 | 14 | 2014-10-20
| Testing Results | 2014-10-06 | 14 | 2014-10-20
Iteration 3 |  | 2014-10-20 | 14 | 2014-11-03
| Iteration Plan | 2014-11-03 | 14 | 2014-11-17
| Aims | 2014-11-03 | 14 | 2014-11-17
| Design | 2014-11-03 | 14 | 2014-11-17
| Design Test Cases | 2014-11-03 | 14 | 2014-11-17
| Usecases | 2014-11-03 | 14 | 2014-11-17
Carer/Patient home screen
De-activate user account
De-activate user account
Contingency Time
Iteration 4
Enable Carer to search for patient
Enable carer to request responsibility of patient
Enable patient to acccept and 'connect' to carer
Enable Carer to search for patient
Enable carer to request responsibility of patient
Enable patient to acccept and 'connect' to carer
Iteration 5
Add medication details
Add appointments
Add reminder functionality
Add medication details
Add appointments
Add reminder functionality
Iteration 6
Accessibility Features
Accessibility Features
Interfacing NHS website
Interfacing NHS website
Emergency Alarm activation: patient -> carer
Emergency Alarm activation: patient -> carer
Iteration 7
CHRISTMAS! YAY!
Catching up!
Iteration 8 - 12th Jan
Record and track when medication is taken
Record and track when medication is taken
Remind carer if the patient is low on medication
Remind carer if the patient is low on medication
Track Carer/Patient correspondence
Track Carer/Patient correspondence
Iteration 9
Directions to appointments
Directions to appointments
Ability to record basic health stats (ie. Heartrate, blood pressure, etc.)
Ability to record basic health stats (ie. Heartrate, blood pressure, etc.)
Ability to track basic health stats
Ability to track basic health stats
Iteration 10
Live chat patient/carer
Live chat patient/carer
Poster for the poster fair