## Sheet1
Documentation
| Abstract |  | Charlotte
Research
|  | Market Research | Rich/Steve | Before freshers week
|  | Target Audience | Charlotte/Ben | Before freshers week
Scope
|  | Purpose | Ben | Before freshers week
|  | Objectives | Ben | Before freshers week
| Requirements |  | Stephen | Before freshers week
Schedule
|  | Gannt Chart | Charlotte | Before freshers week
|  | Network Diagram | Stephen | Before freshers week
|  | Use Cases | Rich | Before freshers week
Quality Management
|  | QA Doocument | Ben | Before freshers week
|  | Test Plan |  | Ongoing
Stakeholders
|  | StakeholdderPlan | Rich | Before freshers week
|  | Stakeholder Analysis | Rich | Before freshers week
Change Management
|  | Change Management Plan | Rich | Before freshers week
Risk Management
|  | Project Risk Assessment | Stephen | Before freshers week
|  | Feasibility Study | Stephen | Before freshers week
Justification
|  | Why android? | Charlotte | Before freshers week
|  | Why Agille? | Ben | Before freshers week
|  | Why WebApp/Android?? | Ben | Before freshers week
Iteration 1
Iteration Plan
Aims
Design
Design Test Cases
Database Design
Entity Relationship Diagram
Conceptual Data Model
Logical Data Model
Physical Data Model
Database Creation
Database Testing
Database Test Results
Create web login Screen
Test Login Screen
Iteration 2
Iteration Plan
Aims
Design
Design Test Cases
Create login screen for app
Implement home screen for carers and patients for web.
Implement home screen for carers and patients for app.
Testing
Testing Results

## Sheet2
Just Health Gannt Chart V2
Key
Andriod app development work
Webiste development work
Task Name |  | Start Date | Duration (days) | End Date | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 29/09/2014(Week 1) | 06/10/2014 (Week 2) | 13/10/2014 (Week 3) | 20/10/2014 (Week 4) | 27/10/2014 (Week 5) | 03/11/2014 (Week 6) | 10/11/2014 (Week 7) | 17/11/2014 (Week 8) | 24/11/2014 (Week 9 ) | 01/12/2014 ( Week 10) | 08/12/2014 (Week 11) | 15/12/2014 (Week 12) | 22/12/2014 (Christmas) | 29/12/2014 (Christmas) | 05/01/2015 (Christmas) | 12/01/2015 (Christmas) | 19/01/2015 (Week13) | 26/01/2015 (Week 14) | 02/02/2015 (Week 15) | 09/02/2015 (Week 16) | 16/02/2015 (Week 17) | 23/02/2015 (Week 18) | 02/03/2015 (Week 19) | 09/03/2015 (Week 20) | 16/03/2015 (Week 21)
Documentation and Planning |  | 2014-08-06 | 47 | 2014-09-22
Abstract
| Research | 2014-08-06 | 28 | 2014-09-03
| Market Research | 2014-08-06 | 28 | 2014-09-03
| Target Audience | 2014-08-06 | 28 | 2014-09-03
| Scope | 2014-08-04 | 49 | 2014-09-22
| Purpose | 2014-08-04 | 49 | 2014-09-22
| Objectives | 2014-08-04 | 49 | 2014-09-22
| Gather Requirements | 2014-08-06 | 47 | 2014-09-22
| Schedule | 2014-08-03 | 50 | 2014-09-22
| Gannt Chart | 2014-08-03 | 50 | 2014-09-22
| Network Diagram | 2014-08-03 | 50 | 2014-09-22
| Legal Documentation | 2014-08-03 | 50 | 2014-09-22
| Quality Management | 2014-08-03 | 50 | 2014-09-22
| QA Document | 2014-08-03 | 50 | 2014-09-22
| Test Plan Document | 2014-08-03 | 50 | 2014-09-22
| Stakeholders | 2014-08-03 | 50 | 2014-09-22
| Stakeholder Plan | 2014-08-03 | 50 | 2014-09-22
| Stakeholder Analysis | 2014-08-03 | 50 | 2014-09-22
| Change Management | 2014-08-03 | 50 | 2014-09-22
| Change Management Plan | 2014-08-03 | 50 | 2014-09-22
| Risk Management | 2014-08-03 | 50 | 2014-09-22
| Project Risk Assessment | 2014-08-03 | 50 | 2014-09-22
| Feasibility Study | 2014-08-03 | 50 | 2014-09-22
| Justification | 2014-08-03 | 50 | 2014-09-22
| Why android? | 2014-08-03 | 50 | 2014-09-22
| Why Agile? | 2014-08-03 | 50 | 2014-09-22
| Why WebApp/Android? | 2014-08-03 | 50 | 2014-09-22
| Issue tracking template and documentation | 2014-09-22 | 7 | 2014-09-29
| Questionnaires | 2014-09-22 | 7 | 2014-09-29
Iteration 1 |  | 2014-09-29 | 14 | 2014-10-13
| Iteration Plan | 2014-09-29 | 7 | 2014-10-06
| Aims | 2014-09-29 | 7 | 2014-10-06
| Design | 2014-09-29 | 7 | 2014-10-06
| Test plan | 2014-09-29 | 7 | 2014-10-06
| Design Test Cases | 2014-09-29 | 7 | 2014-10-06
| Usecases | 2014-09-29 | 7 | 2014-10-06
| Password Research | 2014-09-29 | 7 | 2014-10-06
| Database Design | 2014-09-29 | 7 | 2014-10-06
| Entity Relationship Diagram | 2014-09-29 | 7 | 2014-10-06
| Conceptual Data Model | 2014-09-29 | 7 | 2014-10-06
| Logical Data Model | 2014-09-29 | 7 | 2014-10-06
| Physical Data Model | 2014-09-29 | 7 | 2014-10-06
| Database Creation | 2014-09-29 | 14 | 2014-10-13
| Database Testing | 2014-09-29 | 14 | 2014-10-13
| Database Test Results | 2014-09-29 | 14 | 2014-10-13
| Create Profile and Register | 2014-09-29 | 14 | 2014-10-13
| Create login Screen | 2014-09-29 | 14 | 2014-10-13
| Test Login Screen | 2014-09-29 | 14 | 2014-10-13
Iteration 2 |  | 2014-10-13 | 14 | 2014-10-27
| Iteration Plan | 2014-10-13 | 7 | 2014-10-20
| Aims | 2014-10-13 | 7 | 2014-10-20
| Design | 2014-10-13 | 7 | 2014-10-20
| Test Plan | 2014-10-13 | 7 | 2014-10-20
| Design Test Cases | 2014-10-13 | 7 | 2014-10-20
| Usecases | 2014-10-13 | 7 | 2014-10-20
| Create Profile and Register | 2014-10-13 | 14 | 2014-10-27
| Create login screen | 2014-10-13 | 14 | 2014-10-27
| Patient/Carer home screen | 2014-10-13 | 14 | 2014-10-27
| Testing | 2014-10-13 | 14 | 2014-10-27
| Testing Results | 2014-10-13 | 14 | 2014-10-27
Iteration 3 |  | 2014-10-27 | 14 | 2014-11-10
| Iteration Plan | 2014-10-27 | 7 | 2014-11-03
| Aims | 2014-10-27 | 7 | 2014-11-03
| Design | 2014-10-27 | 7 | 2014-11-03
| Design Test Cases | 2014-10-27 | 7 | 2014-11-03
| Usecases | 2014-10-27 | 7 | 2014-11-03
| Carer/Patient home screen | 2014-10-27 | 14 | 2014-11-10
| De-activate user account | 2014-10-27 | 14 | 2014-11-10
| De-activate user account | 2014-10-27 | 14 | 2014-11-10
| Contingency Time | 2014-10-27 | 14 | 2014-11-10
Iteration 4 |  | 2014-11-10 | 14 | 2014-11-24
| Iteration Plan | 2014-11-10 | 7 | 2014-11-17
| Aims | 2014-11-10 | 7 | 2014-11-17
| Design | 2014-11-10 | 7 | 2014-11-17
| Test plan | 2014-11-10 | 7 | 2014-11-17
| Design Test Cases | 2014-11-10 | 7 | 2014-11-17
| Usecases | 2014-11-10 | 7 | 2014-11-17
| Enable Carer to search for patient | 2014-11-10 | 14 | 2014-11-24
| Enable carer to request responsibility of patient | 2014-11-10 | 14 | 2014-11-24
| Enable patient to acccept and 'connect' to carer | 2014-11-10 | 14 | 2014-11-24
| Enable Carer to search for patient | 2014-11-10 | 14 | 2014-11-24
| Enable carer to request responsibility of patient | 2014-11-10 | 14 | 2014-11-24
| Enable patient to acccept and 'connect' to carer | 2014-11-10 | 14 | 2014-11-24
Iteration 5 |  | 2014-11-24 | 14 | 2014-12-08
| Iteration Plan | 2014-11-24 | 7 | 2014-12-01
| Aims | 2014-11-24 | 7 | 2014-12-01
| Design | 2014-11-24 | 7 | 2014-12-01
| Test plan | 2014-11-24 | 7 | 2014-12-01
| Design Test Cases | 2014-11-24 | 7 | 2014-12-01
| Usecases | 2014-11-24 | 7 | 2014-12-01
| Add medication details | 2014-11-24 | 14 | 2014-12-08
| Add appointments | 2014-11-24 | 14 | 2014-12-08
| Add reminder functionality | 2014-11-24 | 14 | 2014-12-08
| Add medication details | 2014-11-24 | 14 | 2014-12-08
| Add appointments | 2014-11-24 | 14 | 2014-12-08
| Add reminder functionality | 2014-11-24 | 14 | 2014-12-08
Iteration 6 |  | 2014-12-08 | 14 | 2014-12-22
| Iteration Plan | 2014-12-08 | 7 | 2014-12-15
| Aims | 2014-12-08 | 7 | 2014-12-15
| Design | 2014-12-08 | 7 | 2014-12-15
| Test plan | 2014-12-08 | 7 | 2014-12-15
| Design Test Cases | 2014-12-08 | 7 | 2014-12-15
| Usecases | 2014-12-08 | 7 | 2014-12-15
| Accessibility Features | 2014-12-08 | 14 | 2014-12-22
| Accessibility Features | 2014-12-08 | 14 | 2014-12-22
| Interfacing NHS website | 2014-12-08 | 14 | 2014-12-22
| Interfacing NHS website | 2014-12-08 | 14 | 2014-12-22
| Emergency Alarm activation: patient -> carer | 2014-12-08 | 14 | 2014-12-22
| Emergency Alarm activation: patient -> carer | 2014-12-08 | 14 | 2014-12-22
Iteration 7 |  | 2014-12-22 | 21 | 2015-01-12
| CHRISTMAS! YAY! | 2014-12-22 | 21 | 2015-01-12
| Catching up! | 2014-12-22 | 21 | 2015-01-12
Iteration 8 - 12th Jan |  | 2015-01-12 | 14 | 2015-01-26
| Iteration Plan | 2015-01-12 | 7 | 2015-01-19
| Aims | 2015-01-12 | 7 | 2015-01-19
| Design | 2015-01-12 | 7 | 2015-01-19
| Test plan | 2015-01-12 | 7 | 2015-01-19
| Design Test Cases | 2015-01-12 | 7 | 2015-01-19
| Usecases | 2015-01-12 | 7 | 2015-01-19
| Record and track when medication is taken | 2015-01-12 | 14 | 2015-01-26
| Record and track when medication is taken | 2015-01-12 | 14 | 2015-01-26
| Remind carer if the patient is low on medication | 2015-01-12 | 14 | 2015-01-26
| Remind carer if the patient is low on medication | 2015-01-12 | 14 | 2015-01-26
| Track Carer/Patient correspondence | 2015-01-12 | 14 | 2015-01-26
| Track Carer/Patient correspondence | 2015-01-12 | 14 | 2015-01-26
Iteration 9 |  | 2015-01-26 | 14 | 2015-02-09
| Iteration Plan | 2015-01-26 | 7 | 2015-02-02
| Aims | 2015-01-26 | 7 | 2015-02-02
| Design | 2015-01-26 | 7 | 2015-02-02
| Test plan | 2015-01-26 | 7 | 2015-02-02
| Design Test Cases | 2015-01-26 | 7 | 2015-02-02
| Usecases | 2015-01-26 | 7 | 2015-02-02
| Directions to appointments | 2015-01-26 | 14 | 2015-02-09
| Directions to appointments | 2015-01-26 | 14 | 2015-02-09
| Ability to record basic health stats (ie. Heartrate, blood pressure, etc.) | 2015-01-26 | 14 | 2015-02-09
| Ability to record basic health stats (ie. Heartrate, blood pressure, etc.) | 2015-01-26 | 14 | 2015-02-09
| Ability to track basic health stats | 2015-01-26 | 14 | 2015-02-09
| Ability to track basic health stats | 2015-01-26 | 14 | 2015-02-09
Iteration 10 |  | 2015-02-09 | 14 | 2015-02-23
| Iteration Plan | 2015-02-09 | 7 | 2015-02-16
| Aims | 2015-02-09 | 7 | 2015-02-16
| Design | 2015-02-09 | 7 | 2015-02-16
| Test plan | 2015-02-09 | 7 | 2015-02-16
| Design Test Cases | 2015-02-09 | 7 | 2015-02-16
| Usecases | 2015-02-09 | 7 | 2015-02-16
| Live chat patient/carer | 2015-02-09 | 14 | 2015-02-23
| Live chat patient/carer | 2015-02-09 | 14 | 2015-02-23
| Poster for the poster fair | 2015-02-09 | 14 | 2015-02-23
Iteration 11 |  | 2015-02-23 | 14 | 2015-03-09
| Contingency Time | 2015-02-23 | 14 | 2015-03-09