## Sheet1
Issue # | Issue Name | Type | Created By | Assigned To | Start Date | End Date | Description | Status | Resolution | Rich | Resolved
4 | Project Risk Management Plan | Documentation | Rich | Stephen | 2014-09-15 | 2014-09-25 | Document describing how we will manage risks faced by the project | Resolved | Risk management plan has been reviewed by the team and subsequently this issue/task is closed. | Charlotte | Open | Bug
9 | Why Android | Documentation | Charlotte | Charlotte | 2014-09-15 | 2014-09-27 | Document describing why we chose to develop for the android operating system | Resolved | Completed document | Ben |  | Feature
8 | Target Audience | Documentation | Charlotte | Charlotte | 2014-09-15 | 2014-09-27 | Document describing our target audience | Resolved | Completed document | Stephen |  | Documentation
2 | Stakeholder Analysis | Documentation | Rich | Rich | 2014-09-14 | 2014-09-28 | Document describing the various stakeholders of the project and our strategy for them | Resolved | Completed document |  |  | Other