## Sheet1
Documentation
| Abstract |  | Charlotte
Research
|  | Market Research | Rich/Steve | Before freshers week
|  | Target Audience | Charlotte/Ben | Before freshers week
Scope
|  | Purpose | Ben | Before freshers week
|  | Objectives | Ben | Before freshers week
| Requirements |  | Stephen | Before freshers week
Schedule
|  | Gannt Chart | Charlotte | Before freshers week
|  | Network Diagram | Stephen | Before freshers week
|  | Use Cases | Rich | Before freshers week
Quality Management
|  | QA Doocument | Ben | Before freshers week
|  | Test Plan |  | Ongoing
Stakeholders
|  | StakeholdderPlan | Rich | Before freshers week
|  | Stakeholder Analysis | Rich | Before freshers week
Change Management
|  | Change Management Plan | Rich | Before freshers week
Risk Management
|  | Project Risk Assessment | Stephen | Before freshers week
|  | Feasibility Study | Stephen | Before freshers week
Justification
|  | Why android? | Charlotte | Before freshers week
|  | Why Agille? | Ben | Before freshers week
|  | Why WebApp/Android?? | Ben | Before freshers week
Iteration 1
Iteration Plan
Aims
Design
Design Test Cases
Database Design
Entity Relationship Diagram
Conceptual Data Model
Logical Data Model
Physical Data Model
Database Creation
Database Testing
Database Test Results
Create web login Screen
Test Login Screen
Iteration 2
Iteration Plan
Aims
Design
Design Test Cases
Create login screen for app
Implement home screen for carers and patients for web.
Implement home screen for carers and patients for app.
Testing
Testing Results

## Sheet2
Just Health Gannt Chart V2
Task Name |  | Start Date | Duration (days) | End Date | 2014-08-04 | 2014-08-11 | 2014-08-18 | 2014-08-25 | 2014-09-01 | 2014-09-08 | 2014-09-15 | 2014-09-22 | 29/09/2014(Week 1) | 06/10/2014 (Week 2) | 13/10/2014 (Week 3) | 20/10/2014 (Week 4) | 27/10/2014 (Week 5) | 03/11/2014 (Week 6) | 10/11/2014 (Week 7) | 17/11/14 (Week 8) | 24/11/14 (Week 9)
Documentation and Planning |  | 2014-08-06 | 47 | 2014-09-22
Abstract
| Research | 2014-08-06 | 28 | 2014-09-03
| Market Research | 2014-08-06 | 28 | 2014-09-03
| Target Audience | 2014-08-06 | 28 | 2014-09-03
| Scope | 2014-08-04 | 49 | 2014-09-22
| Purpose | 2014-08-04 | 49 | 2014-09-22
| Objectives | 2014-08-04 | 49 | 2014-09-22
| Gather Requirements | 2014-08-06 | 47 | 2014-09-22
| Schedule | 2014-08-03 | 50 | 2014-09-22
| Gannt Chart | 2014-08-03 | 50 | 2014-09-22
| Network Diagram | 2014-08-03 | 50 | 2014-09-22
| Legal Documentation | 2014-08-03 | 50 | 2014-09-22
| Quality Management | 2014-08-03 | 50 | 2014-09-22
| QA Doocument | 2014-08-03 | 50 | 2014-09-22
| Test Plan | 2014-08-03 | 50 | 2014-09-22
| Stakeholders | 2014-08-03 | 50 | 2014-09-22
| StakeholdderPlan | 2014-08-03 | 50 | 2014-09-22
| Stakeholder Analysis | 2014-08-03 | 50 | 2014-09-22
| Change Management | 2014-08-03 | 50 | 2014-09-22
| Change Management Plan | 2014-08-03 | 50 | 2014-09-22
| Risk Management | 2014-08-03 | 50 | 2014-09-22
| Project Risk Assessment | 2014-08-03 | 50 | 2014-09-22
| Feasibility Study | 2014-08-03 | 50 | 2014-09-22
| Justification | 2014-08-03 | 50 | 2014-09-22
| Why android? | 2014-08-03 | 50 | 2014-09-22
| Why Agille? | 2014-08-03 | 50 | 2014-09-22
| Why WebApp/Android?? | 2014-08-03 | 50 | 2014-09-22
| Issue tracking template and documentation | 2014-09-22 | 7 | 2014-09-29
| Questionnaires | 2014-09-22 | 7 | 2014-09-29
Iteration 1 |  | 2014-09-22 | 14 | 2014-10-06
| Iteration Plan | 2014-09-22 | 14 | 2014-10-06
| Aims | 2014-09-22 | 14 | 2014-10-06
| Design | 2014-09-22 | 14 | 2014-10-06
| Test plan | 2014-09-22 | 14 | 2014-10-06
| Design Test Cases | 2014-09-22 | 14 | 2014-10-06
| Usecases | 2014-09-22 | 14 | 2014-10-06
Password Research
| Database Design | 2014-09-22 | 14 | 2014-10-06
| Entity Relationship Diagram | 2014-09-22 | 14 | 2014-10-06
| Conceptual Data Model | 2014-09-22 | 14 | 2014-10-06
| Logical Data Model | 2014-09-22 | 14 | 2014-10-06
| Physical Data Model | 2014-09-22 | 14 | 2014-10-06
| Database Creation | 2014-09-22 | 14 | 2014-10-06
| Database Testing | 2014-09-22 | 14 | 2014-10-06
| Database Test Results | 2014-09-22 | 14 | 2014-10-06
| Basic registration screen | 2014-09-22 | 14 | 2014-10-06
| Create web login Screen | 2014-09-22 | 14 | 2014-10-06
| Test Login Screen | 2014-09-22 | 14 | 2014-10-06
Iteration 2 |  | 2014-10-06 | 14 | 2014-10-20
| Iteration Plan | 2014-10-06 | 14 | 2014-10-20
| Aims | 2014-10-06 | 14 | 2014-10-20
| Design | 2014-10-06 | 14 | 2014-10-20
Test Plan
| Design Test Cases | 2014-10-06 | 14 | 2014-10-20
| Usecases | 2014-10-06 | 14 | 2014-10-20
| Create login screen for app | 2014-10-06 | 14 | 2014-10-20
| Implement home screen for carers and patients for web. | 2014-10-06 | 14 | 2014-10-20
| Implement home screen for carers and patients for app. | 2014-10-06 | 14 | 2014-10-20
| Testing | 2014-10-06 | 14 | 2014-10-20
| Testing Results | 2014-10-06 | 14 | 2014-10-20
Iteration 3 |  | 2014-10-20 | 14 | 2014-11-03
| Iteration Plan | 2014-11-03 | 14 | 2014-11-17
| Aims | 2014-11-03 | 14 | 2014-11-17
| Design | 2014-11-03 | 14 | 2014-11-17
| Design Test Cases | 2014-11-03 | 14 | 2014-11-17
| Usecases | 2014-11-03 | 14 | 2014-11-17