## Sheet1
Risk Management Log
Risk ID | High/Med/Low Risk | Risk Description | Owner | Risk Likelihood | Risk Impact | Risk Index | Risk Category | Risk Mitigation Approach | Risk Mitigation Plan | Risk Expiry Date | Resolution | Resolution Date
1 | Medium Risk | Man in the middle attack on all senstive data | Stephen Tate | 2 | 5 | 10 | External Influences | Mitigate | Encrypt all sensitive data (23/9/14) ¦ This is to be completed when HTTPS is implemented (19/01/15) | 2015-02-22
2 | Low Risk | Device compatibility using Android 2.3 and above | Stephen Tate | 5 | 1 | 5 | Technical | Retain | Advise people to upgrade android version (23/9/14) ¦ Design decisions may change this (19/01/15) | 2015-01-18
3 | Low Risk | Carers misusing patient data | Stephen Tate | 1 | 5 | 5 | People | Transfer | carers are legally bound not to misuse patient data (23/9/14) | 2014-12-19 | Yes | 18.12.14
4 | Medium Risk | Application permissions elevation on android | Stephen Tate | 3 | 3 | 9 | People | Retain | Try to build the app with robustness (23/9/14) ¦ This needs to be retained user is warned upon installation. (19/01/2015) | 2014-12-19 | Yes | 2014-01-19
5 | Low Risk | DPA law changes | Stephen Tate | 1 | 5 | 5 | Legal | Mitigate | Keep an eye on the DPA and ensure we react to any changes quickly (23/9/14) | 2015-03-19
6 | Medium Risk | SQL injection attacks | Stephen Tate | 3 | 5 | 15 | External Influences | Mitigate | Use libraries prevent injections as no direct SQL is used (23/9/14) | 2014-12-19 | Yes | 18.12.14
7 | Low Risk | Denial-of-service (DDoS) attack | Stephen Tate | 2 | 3 | 6 | External Influences | Transfer | Back end infrastructure will be hosted by the university (23/9/14) | 2014-12-19 | Yes | 18.12.14
8 | High Risk | Loss of data | Stephen Tate | 4 | 5 | 20 | Technical | Mitigate | Regular backups and all work stored on our repository as well as raptor (23/9/14) | 2014-12-19 | Yes | 2014-12-18
9 | Medium Risk | Lack of necessary skills, failure to create andrioid app | Stephen Tate | 3 | 5 | 15 | Technical | Mitigate | Use avaliable resources, online tutorials, books and google API's (23/9/14) | 2014-12-19 | Yes | 2014-12-18
10 | Low Risk | Loss of resources group members falling ill or dropping out | Stephen Tate | 1 | 4 | 4 | People | Retain | Adapt to the situation by taking on extra work and accessing realistic goals (23/9/14) | 2015-03-20
11 | High Risk | CS Admin not providing database in time | Stephen Tate | 4 | 5 | 20 | External Influences | Avoid | Remotely hosting database (6/10/14) | 2014-10-12 | Yes | 2014-10-12
12 | Medium Risk | Duplicate effort testing remote and cs admin database | Stephen Tate | 4 | 3 | 12 | People | Mitigate | Scripts will be saved electronically to minimise time this takes (6/10/14) | 2014-10-12 | Yes | 2014-10-12
13 | Medium Risk | Finish Iteration 1 Late causing iteration 2 to finish behind time | Charlotte Hutchinson | 3 | 3 | 9 | People | Mitigate | Work longer hours to keep up with work (20/10/14) | 2014-10-26 | Yes | 2014-10-27
14 | Low Risk | Ben having an operation, unable to work for a while | Charlotte Hutchinson | 1 | 4 | 4 | People | Mitigate | Contingincy plan in place, Ben able to work at home, Charlotte, Steve and Rich taking on more work | 2014-11-02 | Yes | 2014-10-27
15 | Medium Risk | HTTPS not implemented | Richard Logan | 3 | 5 | 15 | Technical | Mitigate | Implement HTTPS (20/10/14) ¦ TBC issue with Nginx, contacting IT Help (19/01/2015), Implemented although HTTP does not redirect to HTTPS (26/01/2015) | 2015-01-22 | Yes | 2015-01-26
16 | Medium Risk | Re designing the databasse | Charlotte Hutchinson | 5 | 2 | 10 | Technical | Retain | Use project week to do this work as well as keep on top of iteration 3 (3/11/14) | 2014-11-09 | Yes | 2014-11-09
17 | High Risk | Anyone can query our API's via POST request | Stephen Tate | 5 | 5 | 25 | Technical | Mitigate | Implement authentication tokens (6/11/14) ¦ HTTP Basic implemented (19/01/2015) | 2014-01-19 | Yes | 2014-01-19
18 | Medium Risk | Security of patient/ carer connection | Charlotte Hutchinson | 3 | 5 | 15 | Technical | Mitigate | Look into ways to do this securely taking into account industry standards (10/11/14) | 2014-11-30 | Yes | 2014-11-24
19 | Low Risk | Security of patient/ carer connection (2) | Charlotte Hutchinson | 1 | 5 | 5 | External Influences | Retain | We have implemented a pin code that would need to be entered in manually, mitigating the risk of someone being able to technically attack it. Although this is still subject to social engineering attacks | 2014-11-24 | Yes | 2015-01-19
20 | Medium Risk | Email only allows 10 bounces a day | Charlotte Hutchinson | 3 | 4 | 12 | External Influences | Retain | We validate all emails using javaScript | 2015-03-20
21 | High Risk | Credentials not encrypted on the android app | Stephen Tate | 5 | 5 | 25 | Technical | Mitigate | Stephen to implement over christmas ¦ Issues experienced with encryption, TBC (19/01/2015) | 2015-02-02
22 | High Risk | API Security is such that anyone that can authenticate with the application is able to make any requests change anything on the application. | Stephen Tate | 4 | 5 | 20 | Technical | Mitigate | Implement methods to check who they are and what they are trying to change | 2015-02-22
23 | Medium Risk | Push Notifications - Unable to use googles service | Richard Logan | 3 | 3 | 9 | Technical | Retain | If we are unable to implement, it will cause a significant impact to the android application. It will take us longer to implement, causing a possible delay to the project | 2015-02-15
24
25
26
27
28
Note on L4: Charlotte Hutchinson: 18.12.14- extending the expiry date to 18 Jan
Note on L5: Charlotte Hutchinson: closed after christmas once user documentation is complete
Note on L7: Charlotte Hutchinson: Leaving open we neeed to research impact of this
Note on L11: Charlotte Hutchinson: Raport has this covered
Note on L18: Charlotte Hutchinson: This is not going to be implemented as there are certificate issues on raptor. Explainations can be found in the technical documentation. Essentially, if we were deploying to our own server we would be able to implement HTTPS.