## Sheet1
Risk Management Log
Risk ID | High/Med/Low Risk | Risk Description | Owner | Risk Likelihood | Risk Impact | Risk Index | Risk Category | Risk Mitigation Approach | Risk Mitigation Plan | Risk Expiry Date | Resolution | Resolution Date
1 | Medium Risk | Man in the middle attack on all senstive data | Stephen Tate | 2 | 5 | 10 | External Influences | Mitigate | Encrypt all sensitive data (23/9/14) | 2015-01-18
2 | Low Risk | Device compatibility using Android 2.3 and above | Stephen Tate | 5 | 1 | 5 | Technical | Retain | Advise people to upgrade android version (23/9/14) | 2015-01-18
3 | Low Risk | Carers misusing patient data | Stephen Tate | 1 | 5 | 5 | People | Transfer | carers are legally bound not to misuse patient data (23/9/14) | 2014-12-19 | Yes | 18.12.14
4 | Medium Risk | Application permissions elevation on android | Stephen Tate | 3 | 3 | 9 | People | Avoid | Try to build the app with robustness (23/9/14) | 2014-12-19
5 | Low Risk | DPA law changes | Stephen Tate | 1 | 5 | 5 | Legal | Mitigate | Keep an eye on the DPA and ensure we react to any changes quickly (23/9/14) | 2015-03-19
6 | Medium Risk | SQL injection attacks | Stephen Tate | 3 | 5 | 15 | External Influences | Mitigate | Use libraries prevent injections as no direct SQL is used (23/9/14) | 2014-12-19 | Yes | 18.12.14
7 | Low Risk | Denial-of-service (DDoS) attack | Stephen Tate | 2 | 3 | 6 | External Influences | Transfer | Back end infrastructure will be hosted by the university (23/9/14) | 2014-12-19 | Yes | 18.12.14
8 | High Risk | Loss of data | Stephen Tate | 4 | 5 | 20 | Technical | Mitigate | Regular backups and all work stored on our repository as well as raptor (23/9/14) | 2014-12-19 | Yes | 2014-12-18
9 | Medium Risk | Lack of necessary skills, failure to create andrioid app | Stephen Tate | 3 | 5 | 15 | Technical | Mitigate | Use avaliable resources, online tutorials, books and google API's (23/9/14) | 2014-12-19 | Yes | 2014-12-18
10 | Low Risk | Loss of resources group members falling ill or dropping out | Stephen Tate | 1 | 4 | 4 | People | Retain | Adapt to the situation by taking on extra work and accessing realistic goals (23/9/14) | 2015-03-20
11 | High Risk | CS Admin not providing database in time | Stephen Tate | 4 | 5 | 20 | External Influences | Avoid | Remotely hosting database (6/10/14) | 2014-10-12 | Yes | 2014-10-12
12 | Medium Risk | Duplicate effort testing remote and cs admin database | Stephen Tate | 4 | 3 | 12 | People | Mitigate | Scripts will be saved electronically to minimise time this takes (6/10/14) | 2014-10-12 | Yes | 2014-10-12
13 | Medium Risk | Finish Iteration 1 Late causing iteration 2 to finish behind time | Charlotte Hutchinson | 3 | 3 | 9 | People | Mitigate | Work longer hours to keep up with work (20/10/14) | 2014-10-26 | Yes | 2014-10-27
14 | Low Risk | Ben having an operation, unable to work for a while | Charlotte Hutchinson | 1 | 4 | 4 | People | Mitigate | Contingincy plan in place, Ben able to work at home, Charlotte, Steve and Rich taking on more work | 2014-11-02 | Yes | 2014-10-27
15 | Medium Risk | HTTPS not implemented | Richard Logan | 3 | 5 | 15 | Technical | Mitigate | Implement HTTPS (20/10/14) | 2015-01-18
16 | Medium Risk | Re designing the databasse | Charlotte Hutchinson | 5 | 2 | 10 | Technical | Retain | Use project week to do this work as well as keep on top of iteration 3 (3/11/14) | 2014-11-09 | Yes | 2014-11-09
17 | High Risk | Anyone can query our API's via POST request | Stephen Tate | 5 | 5 | 25 | Technical | Mitigate | Implement authentication tokens (6/11/14)
18 | Medium Risk | Security of patient/ carer connection | Charlotte Hutchinson | 3 | 5 | 15 | Technical | Mitigate | Look into ways to do this securely taking into account industry standards (10/11/14) | 2014-11-30 | Yes | 2014-11-24
19 | Low Risk | Security of patient/ carer connection (2) | Charlotte Hutchinson | 1 | 5 | 5 | External Influences | Retain | We have implemented a pin code that would need to be entered in manually, mitigating the risk of someone being able to technically attack it. Although this is still subject to social engineering attacks | 2014-11-24
20 | Medium Risk | Email only allows 10 bounces a day | Charlotte Hutchinson | 3 | 4 | 12 | External Influences | Retain | We validate all emails using javaScript | 2014-12-19
21 | High Risk | Credentials not encrypted on the android app | Stephen Tate | 5 | 5 | 25 | Technical | Mitigate | Stephen to implement over christmas | 2015-01-20
22
23
24
25
26
27
28
Note on L4: Charlotte Hutchinson: 18.12.14- extending the expiry date to 18 Jan
Note on L5: Charlotte Hutchinson: closed after christmas once user documentation is complete
Note on L7: Charlotte Hutchinson: Leaving open we neeed to research impact of this
Note on L11: Charlotte Hutchinson: Raport has this covered
Note on L18: Charlotte Hutchinson: Implemeted over christmas