## Sheet1
Risk Management Log
Risk ID | High/Med/Low Risk | Risk Description | Owner | Risk Likelihood | Risk Impact | Risk Index | Risk Category | Risk Mitigation Approach | Risk Mitigation Plan | Risk Expiry Date
1 | Medium Risk | Man in the middle attack | Stephen Tate | 2 | 5 | 10 | External Influences | Mitigate | Encrypt all sensitive data 23/9/14 | 2014-12-19
2 | Low Risk | Device compatibility | Stephen Tate | 5 | 1 | 5 | Technical | Retain | Advise people to upgrade android version 23/9/14 | 2014-12-19
3 | Low Risk | Carers misusing patient data | Stephen Tate | 1 | 5 | 5 | People | Transfer | carers are legally bound not to misuse patient data | 2014-12-19
4 | Medium Risk | Application permissions elevation on android | Stephen Tate | 3 | 3 | 9 | People | Avoid | Try to build the app with robustness | 2014-12-19
5 | Low Risk | DPA law changes | Stephen Tate | 1 | 5 | 5 | Legal | Mitigate | Keep an eye on the DPA and ensure we react to any changes quickly | 2014-12-19
6 | Medium Risk | SQL injection | Stephen Tate | 3 | 5 | 15 | External Influences | Mitigate | Use libraries prevent injections as no direct SQL is used | 2014-12-19
7 | Low Risk | DDoS | Stephen Tate | 2 | 3 | 6 | External Influences | Transfer | Back end infrastructure will be hosted by the university | 2014-12-19
8 | High Risk | Loss of data | Stephen Tate | 4 | 5 | 20 | Technical | Mitigate | Regular backups | 2014-12-19
9 | Medium Risk | Lack of necessary skills | Stephen Tate | 3 | 5 | 15 | Technical | Mitigate | Use avaliable resources | 2014-12-19
10 | Low Risk | Loss of resources | Stephen Tate | 1 | 4 | 4 | People | Retain | Adapt to the situation | 2014-12-19
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28