## Trello_Cards_Export
Trello ¦ JustHealth Issue Management [CSV file generated and exported from Trello]
ID | Story | Description | Comments | Members | Checklist | Labels | Due Date
1 | Organise GitHub |  |  |  |  | Android | 2014-10-06T11:00:00.000Z
2 | QA Document |  |  |  |  | Android Completed
3 | High-level Design Document |  |  |  |  | Android | 2014-10-06T11:00:00.000Z
4 | Purpose/Objectives |  |  |  |  | Android Completed
5 | Coversheet Template |  |  |  |  | Android | 2014-10-06T11:00:00.000Z
6 | High-res Logo |  |  |  |  | Android Completed
7 | Tracking Document |  |  | Rich Logan |  | Completed | 2014-10-06T11:00:00.000Z
8 | DB Design |  |  | Stephen Tate |  | Completed Documentation
9 | Usecases |  |  | Rich Logan |  | Completed | 2014-10-06T11:00:00.000Z
10 | Why Agile Methodologies |  |  | Rich Logan |  | Completed | 2014-10-06T22:59:00.000Z
11 | Network Diagram |  |  | Stephen Tate |  | Testing Completed
12 | Legal Docs |  |  | Stephen Tate |  | Testing | 2014-10-06T11:00:00.000Z
13 | Requirements by User |  |  | Stephen Tate |  | Testing | 2014-10-06T11:00:00.000Z
14 | Test Cases/Test Plan |  |  | Stephen Tate |  | Testing | 2014-10-06T11:00:00.000Z
15 | Email Caroline |  |  | Stephen Tate |  | Testing | 2014-10-06T11:00:00.000Z
16 | Gantt Chart |  |  |  |  | Database | 2014-10-06T11:00:00.000Z
17 | Questionnaire Results |  |  | Rich Logan |  | Completed
18 | Iteration 1 Plan |  |  | Charlotte Hutchinson |  | Database | 2014-10-06T11:00:00.000Z
19 | Role Documentation |  |  | Charlotte Hutchinson |  | Database | 2014-10-06T11:00:00.000Z
20 | Password Research |  |  | Charlotte Hutchinson |  | Database | 2014-10-06T11:00:00.000Z
21 | Feasibility Study |  |  | Charlotte Hutchinson |  | Database | 2014-10-06T11:00:00.000Z
22 | Test cases |  |  | Stephen Tate |  | Testing | 2014-10-06T08:00:00.000Z
23 | Questionnaires |  |  | Rich Logan Stephen Tate |  | Completed Documentation
24 | Update research |  |  | Rich Logan |  | Documentation
25 | Fix JS link |  |  | Rich Logan |  | Completed Web
26 | Initial Documentation |  |  | Rich Logan |  | Documentation
27 | Android Layout |  |  | Rich Logan |  | Android
28 | Commit Empty Android Project |  |  | Rich Logan |  | Android Completed
29 | Update Gantt chart |  |  | Stephen Tate |  | Completed Documentation
30 | Ajax on username | Inform the user on registration if a username is already taken as they type |  | Rich Logan | API Call https://github.com/RichLogan/JustHealth/commit/69f2c71f558cabe41239a4480792cb5c57a96fb2 Ajax | Web Completed
31 | Complete iteration 1 testing |  |  | Stephen Tate Rich Logan Charlotte Hutchinson |  | Testing Completed Web
33 | Technical Document |  |  | Rich Logan |  | Documentation
34 | Export Issues/Trello to CSV | https://github.com/RichLogan/trello-export works nicely for Trello -> CSV export. JSON export can be found from Trello Menu->Export->JSON |  | Rich Logan | Trello Github | Documentation
35 | Add DB Design into plan |  |  | Rich Logan Stephen Tate |  | Completed Documentation
36 | Layout, input buttons, btn-success etc etc |  |  |  |  | Completed Web
37 | User and Maintenance Documentation |  |  | Rich Logan Stephen Tate Ben McGregor Charlotte Hutchinson |  | Documentation Android Database Web
38 | GitHub: Low/Med/High Priority |  |  | Rich Logan |  | Completed Documentation
39 | JS Date |  |  | Ben McGregor |  | Completed Web
40 | Add Database design to Iteration 1 plan |  |  | Stephen Tate |  | Completed Documentation
41 | CSS on reg and log in screen (web) |  |  | Ben McGregor |  | Completed Web
42 | Test Cases |  |  | Ben McGregor Stephen Tate |  | Completed Documentation
43 | Home screen design update |  |  |  |  | Completed Web
44 | Android account locked |  |  | Stephen Tate |  | Completed Android
46 | home screen web html |  |  | Ben McGregor | Patient Carer | Completed Web
47 | Android Register |  |  | Rich Logan Stephen Tate | Core Validation Terms and conditions Check username is not already in the DB Account type list | Android Completed
48 | Corpus stylings |  |  | Rich Logan |  | Documentation Web Completed
49 | Restructure Flask |  |  | Rich Logan |  | Completed Web
50 | Database exceptions | https://github.com/RichLogan/JustHealth/issues/58 |  | Stephen Tate |  | Android API Web Completed
51 | Footer |  |  | Rich Logan |  | Completed Web
52 | Link pages in android |  |  | Rich Logan | Login -> Register Login -> Forgot Password Register -> Terms and Conditions | Android Completed
53 | Forgot Password |  |  | Rich Logan |  | Android Completed
54 | Register option on login |  |  | Charlotte Hutchinson |  | Completed Web
55 | Handle when app is not connected to the internet | http://stackoverflow.com/questions/9570237/android-check-internet-connection | @charlotte352 @richlogan Yes, need to just work out how to do, shouldn't be too hard though. With the Request.post() method it means we only have to do the update in one place. is this a case of an error message coming up saying you are offline? @richloga | Stephen Tate Rich Logan |  | Android Completed
56 | Separate Views and Models |  |  | Rich Logan |  | Completed Android Web
57 | Releases |  | to be done 12th Jan | Stephen Tate |  | Documentation Completed | 2015-01-12T20:00:00.000Z
58 | Front end validation |  |  | Charlotte Hutchinson |  | Completed Android
59 | QA Research |  |  | Ben McGregor |  | Documentation Completed
60 | Design for deactivate account |  |  | Ben McGregor |  | Documentation Android Completed Web
61 | Aims |  |  | Charlotte Hutchinson |  | Documentation Completed
62 | Test Cases |  |  | Rich Logan | Deactivate Account Home Screen Copy over Iteration 1/2 Web Database cases | Testing Completed
63 | Testing |  |  | Charlotte Hutchinson |  | Android Testing Completed Web
64 | Use Cases |  |  | Charlotte Hutchinson |  | Documentation Completed
65 | Account Type Spinner |  |  | Rich Logan |  | Android Completed
66 | Network Diagram |  |  | Stephen Tate |  | Documentation Completed
67 | update iteration 3 plan with assumptions for database |  |  | Charlotte Hutchinson |  | Documentation Completed
68 | android deactivate account screen |  |  | Charlotte Hutchinson |  | Android Completed
69 | Register should have proper alerts, instead HTTP returns |  |  | Rich Logan |  | Completed Web
70 | Raptor Token | Username: Rich Logan Token: 6d28ded0e2419c220df712f7627cc11b085ade84 |  |  |  | Completed
71 | Android- error messages |  |  | Rich Logan | Login | Android Completed
72 | Use case diagram |  |  | Ben McGregor |  | Documentation Completed
73 | Network Diagram |  |  | Stephen Tate |  | Documentation Completed
74 | Project Plan |  |  | Charlotte Hutchinson |  | Documentation Completed
75 | Think of ways to connect users securely |  |  | Charlotte Hutchinson Ben McGregor Rich Logan Stephen Tate |  | Completed
76 | API Automated Testing | This is so long I think it's a christmas situation |  | Rich Logan Stephen Tate Ben McGregor Charlotte Hutchinson | Registration (1) Authenticate (1) Deactivate Reset Get Account Info Lock Account Search Patient Carer (4) Create Connection (4) Complete Connection (4) Delete Connection (4) Cancel Connection (4) Get Connections (4) Rich to add Web and Android tests to portal | Documentation API Testing
77 | Check root view mapping |  |  | Rich Logan |  | Web Completed
79 | Front Page |  |  | Ben McGregor |  | Web Completed
80 | Testing |  |  | Stephen Tate Charlotte Hutchinson |  | Testing Completed
81 | Android search function |  |  | Stephen Tate |  | Android Completed
82 | Https |  | Can't do this without Tim installing nginx for us on Raptor. And since Apache is used on Raptor not even sure if that's possible. Gonna wait until I can talk to Tim about this because if we have to use Apache I don't actually have a clue how to do it.... On the plus side, I know exactly how to do it if/once nginx is installed...I think... | Rich Logan | Flask Dev Server HTTPS Gunicorn HTTPS Load all resources across HTTPS | Android Web Completed
83 | Secure POST's authentication. |  |  | Rich Logan Stephen Tate |  | Android Web
84 | Design |  |  | Ben McGregor | turn to pngs add to design doc add to iteration 4 plan doc add usecases to iteration 4 plan | Documentation Completed
85 | Update database design |  |  | Stephen Tate |  | Database Documentation Completed
86 | Profile |  |  | Charlotte Hutchinson |  | Web Completed
87 | Update Test Plan (portal) |  |  | Stephen Tate |  | Documentation Testing
88 | Web search and connect function |  | I converted the Proper Responses to a card here: https://trello.com/c/lSF0RfVU/154-proper-responses-connections So not yet :D @richlogan @charlotte352 Should this be marked complete? | Rich Logan Charlotte Hutchinson | Search Create Connection Complete Connection Delete Connection Cancel Connection Proper Responses https://trello.com/c/lSF0RfVU/154-proper-responses-connections | Web API Completed
89 | Profile Android |  |  | Ben McGregor Stephen Tate |  | Android Completed
90 | Testing Android and Web |  |  | Charlotte Hutchinson Ben McGregor |  | Testing Completed
91 | Aims
92 | Plan |  |  | Charlotte Hutchinson Ben McGregor Rich Logan Stephen Tate | Aims Design Usecases Network diagram Database Update | Documentation Completed
93 | Usecases
94 | Design
95 | Test Cases |  |  | Ben McGregor |  | Testing Documentation Completed
96 | Android |  |  |  | Add medication details Add appointments Add reminder functionality
97 | Web |  |  |  | Add medication details Add appointments Add reminder functionality
98 | Testing |  | @stephentate1 @richlogan @benmcgregor I have just written these tests and moved some over for our iteration 6 (remember we had that change) for web and android. I will test asap, maybe we could split it up, i dont mind doing the long android and web if |  | Android Web API | Testing
99 | Display results Web in a new tab on profile page |  |  | Rich Logan |  | Web Completed
100 | Display results on android- on a button |  |  | Stephen Tate |  | Android Completed
101 | Deactivate Web |  |  | Rich Logan |  | Web Completed
102 | Deactivate android |  |  | Stephen Tate |  | Android Completed
103 | Header android |  | Done in Android Design https://trello.com/c/xVU95CHR/165-design-android | Ben McGregor |  | Android Completed
104 | Comment all API |  |  | Ben McGregor |  | Documentation Completed
105 | Header Web |  |  | Charlotte Hutchinson |  | Completed Web
106 | Prescriptions |  | Need to do Front End Validation for Add Prescription Unchecking Remove because no confirm. Will add now. | Rich Logan Charlotte Hutchinson | Add Prescription Edit Prescription Remove Prescription View Prescriptions Carer View Prescriptions Patient Front End Validation | Web API
107 | Prescriptions |  | Deletion done: https://github.com/RichLogan/JustHealth/commit/c9ae662b2d955642dbabf09aa7c077cbf9a4845f Now broken down by Active/Upcoming/Expired https://github.com/RichLogan/JustHealth/commit/562b05ebdcac41472435a653e351c4fda247a146 You're right just an admin thing @richlogan when we add pharamsicts they will be able to do this Is 'Remove Medication' and 'Edit Medication' actually a thing? I thought it was an admin kind of thing @charlotte352 | Rich Logan Charlotte Hutchinson | Add Prescription Edit Prescription Remove Prescription View Prescriptions Carer View Prescriptions Patient | Android Completed
108 | Appointments |  |  | Stephen Tate Ben McGregor | Add Remove Update | Android Completed
109 | Appointments |  | @charlotte352 I have fixed this, will let you take a look/test and mark as complete if you are happy with it :) The issue was that carers were able to update/delete appointments that they didn't create. I have disabled the update and delete buttons for t | Stephen Tate Ben McGregor | Carer Add Carer Remove Carer Edit Patient Add Patient Delete Patient Edit Carer/Patient Add Carer/Patient Edit Carer/Patient Delete | Web Completed
110 | Plan |  |  | Charlotte Hutchinson Ben McGregor Stephen Tate | Aims Requirements Design- Ben Use cases- Charlotte Database update- Steve Network Diagram- Steve | Documentation Completed
111 | Test Cases |  |  | Rich Logan Stephen Tate | Android Web API | Testing Documentation
112 | Notifications |  |  |  | connection request (green) connection complete (green) new prescription added for a patient (green) appointment added with you (green) password expiry 10 days before (yellow) password less than 1 day (red) | Android Completed
113 | Notifications |  |  | Rich Logan Stephen Tate | connection request (green) connection complete (green) new prescription added for a patient (green) appointment added with you (green) password expiry 10 days before (yellow) password less than 1 day (red) Appointment Updated Appointment Cancelled Prescription Updated Notify carer when patient is running low on medication | Web Completed
114 | Reminders |  |  | Rich Logan | Appointments- 30 mins before (green) Medication- 15 mins before needs to be taken (green) Appointment- at the time (green) medication at the time (green) See: https://trello.com/c/H3KSrPJj/182-display-medication-taken-to-carer Notify carer when running low | Android
115 | Reminders |  | Basic structure to check if there are appointments to add, and adding appointments is now in place. Automatic add for Appointments working, as does the getReminders method. Needs to be done: - Reminder expiry / delete - Printing out (very small work) - Times for prescriptions I'm going to move on to the other things I've been assigned for this weekend now though. | Rich Logan | Appointments- 30 mins before (green) Appointment- at the time (green) Medication on the day it should be taken Track when medication is taken | Web Completed
116 | Convert all existing long post requests to use PostRequest.post(url, parameters) |  | @charlotte352 @richlogan I'm sure that these have all been converted now. Marking as complete. @charlotte352 Yes, I still think there are a few outstanding but apart from that we are dandy. I will check before closing. @stephentate1 has this been done in | Rich Logan Stephen Tate | Prescriptions Appointments Master Backlog | Android Completed
117 | Testing Portal |  | Yeah :) Yeah we just want to have them as a pdf or something that they can look at I guess @charlotte352 We need to ensure that we can print each test followed by the results nicely :) @stephentate1 What is this one? | Stephen Tate |  | Testing
118 | Test Plan |  |  | Stephen Tate |  | Testing Documentation Completed
119 | Secure POST's authentication. |  | This is in the christmas list now. Archiving. | Rich Logan Stephen Tate |  | Android Web
120 | Implement HTTPS on production |  | Duplicate | Rich Logan |  | API
121 | Implement API authentication |  | @richlogan Thought I had, will do it now. This has been completed and merged to master. Mark as complete? @stephentate1 | Stephen Tate |  | API Completed
122 | Why Agile Document |  | design, test do Need to change the current document to talk about our approach, iterative, 2/3 meetings a week, stay in contact on days we dont meet etc, pair programming, test driven development..... | Charlotte Hutchinson |  | Documentation Completed
123 | Legal |  | If i have time I will change this to modals Site Map completed to the stage it can be at the moment. If have more time may change the design of it. Something extra which would be good to have | Ben McGregor Charlotte Hutchinson | Privacy Policy T & C References/ acknowledgements Site Map? | Documentation Completed
124 | Technical Document- Architecture |  | https://github.com/RichLogan/JustHealth/pull/125 I think that's a good example Pull Request if we want to use one :) Need to break this down into a checklist of everything that needs to be done for the general technical document, maintenance doc and security doc | Rich Logan | why python why peewee why bootstrap why Flask why Android why API/ POST etc Why postgres | Documentation Android
125 | QA all Documents |  |  | Ben McGregor |  | Documentation
126 | JH IM Portal | All of this needs to be graphs! High charts, moment JS, chart JS, D3 JS | I've added pages to cover what's on the checklist, home page is /adminPortal @benmcgregor to set up the web page and let everyone know when this is complete so we can work on parts of the checklist each Are we having a admin interface which shows: - users - and why people deactivate etc | Charlotte Hutchinson Ben McGregor | Usersname list charts on usage why deactivated- reason to be able to add medication name add and remove reasons to deactivate verify users account manually Add new medication Medication list Delete Accounts manually Admin account set up Design change for yang | Web Completed
127 | Design Web and Android |  | @stephentate1 oh hype I'll steal it @richlogan believe I have implemented this in appointments :) Tiny idea for Android design. You know when in some apps and websites you scroll in a section and the heading stays? Might be nice for prescriptions if there | Stephen Tate Ben McGregor |  | Android Web Completed
128 | User Doc |  | $ make HTML That will make a _build directory with the html in @richlogan how to i run my sphinx file? type $ sphinx-build into terminal? then what? how to i find the page? All of the above need to be done for web and android. Will discuss more next weeks meeting | Charlotte Hutchinson | Introduction Registration Verify email login forgot password account locked deactivate account search and connect function appointments for carers and patients, add, edit, delete medication/ prescriptions for add, edit and delete Add since christmas | Documentation
129 | Site Map |  | Do we need this? |  |  | Web Documentation
130 | Questionnaire |  | Finished on google form, all ready to be sent out when released via this link http://goo.gl/forms/hjc2VqckWT send out survey monkey test to people we have given the app / website to | Charlotte Hutchinson |  | Documentation Testing Completed
131 | Deactivate Android |  | @charlotte352 Excellent :) @stephentate1 all finished, I also ran some new tests on the web to double check that still works :) @charlotte352 completed the implementation. This can be tested now. It has been merged to master. When complete @stephentate1 t | Stephen Tate Charlotte Hutchinson | Deactivate android Test deactivate android | Testing Android Completed
132 | Edit profile web and android |  | Change of email should require verification, @richlogan can you set this up on android? | Ben McGregor Rich Logan | Web @benmcgregor Android @richlogan including add profile picture web including profile pic android Edit Profile API | Android Web Completed
134 | Display when connections already established in search |  | @richlogan I have updated what I think is the related issue this evening too. https://github.com/RichLogan/JustHealth/issues/109 Ajax | Rich Logan | Web Android | Web Android Completed
135 | back button web
136 | Corpus index update |  |  | Charlotte Hutchinson |  | Documentation Completed
137 | Test iteration 4 |  | This to be completed once the all the API tests are written |  |  | Testing Completed
138 | Test iteration 5 & 6 |  | There are no iteration 6 tests right? This was the one you replied to @richlogan :) any news? I deleted any tests that were wrong but I think it was mainly 4. I'll look now @richlogan I cant remember if you looked at these or not yet? @richlogan please fix the API tests :) Thanks resolved the syntax errors but still cant seem to get them working. Will talk about this on Monday Both iterations are moved to one as we had the change of moving parts over | Rich Logan | Web Android Database API | Testing
139 | Rich to add his research |  |  | Rich Logan |  | Documentation Completed
140 | Database update |  | What exactly is this? @stephentate1 | Stephen Tate |  | Database Documentation Completed
141 | Update Gantt chart |  | Completed up to the end of iteration 8. Not going to do any more for the time begin incase iteration changes. @charlotte352 Lol, what's happened now? I hate project libre so much @stephentate1 haha You legend @stephentate1 yeah I will fill that all in tomorrow @charlotte352 the issue is with the completed field I think. I have corrected the ones that are wrong really quickly this evening and added a field called % complete. I think it is best if we just manually type when it is 100% complete. That way it will stop breaking it. Doing it the automated way doesn't add any real value anyway so I don't see as we lose anything. Added it as version 7.1 and will commit to master, are you ok to finish filling it in? @charlotte352 I will try to get round to this tomorrow. If not then the day after, will let you know. @stephentate1 I keep getting the same problem that i had on the last day of term. Nothing I am trying seems to be working, if you can (i know you are super busy) could you just have a look for five mins please? | Charlotte Hutchinson |  | Documentation Completed
142 | Support Gravatar |  | Don't have time for this Thinking about this: When loading profile: if picture in DB != NULL: load picture else if has gravatar: pass gravatar picture else: load default picture |  |  | API Not Doing
143 | Add Date/Time pickers in android as opposed to text views |  | http://stackoverflow.com/questions/14933330/datepicker-how-to-popup-datepicker-when-click-on-edittext @charlotte352 thanks! :) @stephentate1 @richlogan I have put what i have done on a branch. Will try a bit more tomorrow and let you know @charlotte352 @richlogan Hmm typical Google documentation.. Is there not a way to resize it in xml? Probably not important to functionality as such, but needs to be done and now is a good time I think. I will have a look later, maybe put what you have done on a branch and we can take a look then? @stephentate1 @richlogan Im struggling with this at the moment, tired yesterday afternoon and for an hour this morning. I can get one in on the register page, but it just looks horrendous on a phone its just too big. Also the documentation doesn't seem to be completely true for whats online. How important do is this at the moment? Android gradel not working at the moment, will try again later | Charlotte Hutchinson |  | Android Not Doing
144 | Security Documentation (a part of the technical) |  |  |  |  | Documentation
145 | Handle Android Version related errors |  | has this been completed too? @richlogan @stephentate1 |  |  | Android Completed
146 | Testing |  |  | Ben McGregor Charlotte Hutchinson | Android API Web | Testing
147 | Technical Document- Security |  | Marking this as complete. HTTPS still is to be completed but need to do this once we have completed implementation. I have also added the javasphinx library to the Technical Documentation. Obviously the Security section will need to be updated as we go. FYI @charlotte352 @richlogan @benmcgregor Virtually completed, just need to add code examples that I am unable to do on my iPad in my break at work. Will try to complete 100% either tonight or tomorrow. :) | Stephen Tate | API authentication HTTPS Password security Database | Documentation Completed
148 | Technical Document- Maintenance |  | Unticking checklist as a lot has been updated since this was marked complete @charlotte352 yeah comment the code and maybe just generally talk about in sphinx? I'm not sure. Look in Documentation/technical there's a readme and examples @richlogan how do you want me to do the HTML part, comment the code then? can this go into Spinx? also where are the current API.rst files so i can look at them for guidance. Stephen- Android Rich- API Ben- Views Charlotte- HTML | Charlotte Hutchinson Ben McGregor Rich Logan Stephen Tate | API Web HTML Android Views | Documentation
149 | Rich- to write a read me doc on how to do sphinx |  |  | Rich Logan |  | Documentation Completed
150 | Profile Pictures |  | Print in the search static website folder make a new folder call profile pictures uploads the file (their username) file name goes into the database select from the view to load |  |  | Web Android
151 | 2 factor authentication |  | No time! |  |  | Not Doing
152 | Keeping a user logged in on android |  | onResume() @charlotte352 Yes, I think that this is along the right lines. Although, we would need to work out how to save the data in the app without the need to refresh. We could do this bit relatively easily I think. Would something like this work do you think @stephentate1 http://stackoverflow.com/questions/12744337/how-to-keep-android-applications-always-be-logged-in-state Not a priority but was just looking into it today | Stephen Tate |  | Android Completed
153 | Mid project review doc |  |  | Charlotte Hutchinson |  | Documentation Completed
154 | Proper Responses (Connections) | Parent: https://trello.com/c/FMOUfZRC/88-web-search-and-connect-function | https://github.com/RichLogan/JustHealth/pull/145 | Rich Logan | Delete | Web Completed
155 | JS to stop people closing when forms are half filled in | You know how most websites won't let you close a window if you have "unsaved" work? Probably one of those little things that is a good idea. Just came to me | definitely a good idea as an added extra @richlogan Probably something like if any inputs.val != Null prevent default on window close |  |  | Web Testing
156 | Stop Android app going back to login screen |  | Only pages that still do this are the both home pages has this been complete with the design update? @stephentate1 @richlogan Possibly to do with all the activities having Login as their parent? | Rich Logan |  | Android Completed
157 | Settings page |  | I have made progress on this for the web. All that is left to do it changing the deactivate api to be included in the settings views | Charlotte Hutchinson | Web Android | Web Android Completed
158 | Iteration 5 Test Cases |  | Including myPatients, carer only, patient only. Also testing for privacy of appointments etc. | Ben McGregor | API Test Cases - this includes medication, appointments and prescriptions Web Tests Android Tests | Testing Completed
159 | Need to be able to log out in the app |  |  |  |  | Android Completed
160 | Authenticating the specific user in the API calls | At the moment as long as your credentials are valid you can do ANYTHING that requires credentials. That is, you can alter prescriptions/appointments/profiles etc that you do not belong to/have ownership. Very much the biggest thing that needs to be fixed at this time. | Potentially a huge security flaw, I think it mainly affects medication, prescriptions, appointments. | Stephen Tate | Raise Risk Discuss a way forward Implementation Reference in the security documentation | API Completed
161 | request.form | Would be nice to change some of the views to request.form instead of split everything up. It's okay when we're just sending request.form['username'] but otherwise. So glad I realised you could do this! |  |  |  | API
162 | Plan |  |  | Ben McGregor Charlotte Hutchinson | Aims Requirements Design Usecases Network diagram | Documentation Completed
163 | Test Cases |  | Re run all previous functionality tests |  |  | Testing Documentation Completed
164 | Design Web |  | @stephentate1 why did you unmark login as complete? | Ben McGregor Charlotte Hutchinson | carer home patient home carer appointments deactivate legal login my patients patient appointments patient update appointment prescriptions privacy policy profile references register reset password search sitemap template terms and conditions Change create appointment button Change delete appointments to a bin FAQ Account Settings Contact | Web Completed
165 | Basic Android Design |  |  | Rich Logan | Login Registration Forgot password Home carer Home patient carer add prescription carer edit prescription carer patient appointments carer personal appointments connections carer prescriptions create carer patient appointment create self appointent deactivate account edit profile my patients Patient Prescriptions privacy profile search self appointments self archive appointments settings T & C Need to be able to log out in the app | Android Completed
166 | Testing |  |  |  |  | Testing Completed
167 | Write up results of questionnaires |  |  | Charlotte Hutchinson |  | Documentation Completed
168 | Flow charts of how the processes work etc. |  |  |  |  | Documentation
169 | check requirements doc and scope |  |  | Charlotte Hutchinson |  | Documentation
170 | SASS? | I guess at this stage it would be purely for marks but still haha. I'd like to learn it though http://sass-lang.com/ | Probably impossible to backwardly do all our CSS to SASS. Shame I didn't think from the start :cry: |  |  | Web Not Doing
171 | AJAX |  |  |  | Register - Username Search Appointment Clash checking | Web
172 | Java commenting |  |  | Charlotte Hutchinson Ben McGregor Rich Logan Stephen Tate | Add Prescriptions Calendar Appointments Carer Patient Appointments Carer Patient Archived appointments Carer Prescriptions Connections Create Carer Patient Appointment Create self appointment deactivate account edit carer patient appointment edit prescription edit profile edit self appointment feedback forgot password home carer home patient login mypatients patient medication privacy Request Search self appointments self archived appointments settings terms and conditions LoadImage Search NHS C2DMRegistrationsReceiver Connections Main Connections View Feedback GcmBroadcastReciver GcmIntentService Logout Main Register Request Profile Carer Add Correspondence Patient carer correspondence | Android Documentation
173 | Restructure | Move all public facing API calls into another file | Tried to do templating on dashboard and it didn't work. More hassle than it's worth. Removing... |  | application.py api.py | API
174 | Add telephone number |  |  | Rich Logan |  | Database API Completed
175 | Link from connections to the connected persons profile |  |  | Charlotte Hutchinson |  | Web API Completed
178 | Plan |  |  | Charlotte Hutchinson Ben McGregor Stephen Tate | Aims- Charlotte Requirements- Charlotte Design- Ben Use cases- Charlotte Database update- Steve Network Diagram- Steve | Documentation Completed
179 | Test Cases |  | @richlogan it is just the automated tests left to do :) I have done all the others | Rich Logan Stephen Tate Charlotte Hutchinson | Search NHS- Web and android Patient carer correspondence Admin portal Track medication taken Stock Levels notify carer Notify carer when patient has not taken medication Automated Tests | Testing Documentation
180 | Search NHS |  |  | Stephen Tate |  | Android Web Completed
181 | Track patient carer correspondence |  | Web done | Charlotte Hutchinson |  | Web Android Completed
182 | Display medication taken to carer |  |  | Rich Logan | Display AJAX boxes for patient to tick Decrease stock levels after taken notify carer when patient stock level drops below X Notify carer when patient hasn't taken medication Android | Android Web
184 | Testing |  |  |  | Web Android API | Testing
185 | Appointments Accept/Decline |  | Completed Web | Stephen Tate |  | Web Android Completed
186 | Technical Report |  | https://moodle.kent.ac.uk/2014/mod/page/view.php?id=112433 |  |  | Documentation
187 | Update Index Corpus |  | I feel this is upto date just need to link all the files now! |  |  | Documentation
188 | Validation |  |  | Ben McGregor |  | Android Web
189 | View appointments android |  |  | Stephen Tate |  | Android Completed
190 | Test Cases |  | There are a lot (the majority) that will not work due to authentication and database changes. This is a bigger task than first thought. Check that all the automated test cases are working and that there are none missing. | Ben McGregor |  | Testing
191 | Add onResume() to android pages - to dynamically reload |  |  | Stephen Tate Rich Logan Charlotte Hutchinson | Update appointments doesnt update unless you go out of appointments and back in | Android Completed
192 | Audit Tables (Triggers on the Database) |  | This is high priority, shows that we have thought outside the box too. |  |  | Database Not Doing
194 | Speed up the app |  |  | Rich Logan Stephen Tate | Passing through objects Async requests where possible packaging and zipalign (research this) | Android Completed
195 | Re test everything |  | All to test on Tuesday 1,2,3,4,5 complete | Stephen Tate Ben McGregor Charlotte Hutchinson Rich Logan |  | Testing Completed
196 | Test cases for security |  |  | Stephen Tate Charlotte Hutchinson Rich Logan |  | Testing
197 | Videos |  |  |  | 1 Someone Registering on the app- just typing in fake details 2a Carer starting on home screen-> clicking on a patient -> adding medication 2b Patient getting the notification of prescription added-> going into view medication and seeing it there 3a Adding an appointment and adding to the native calendar 3b Getting a reminder of your appointment
198 | Add words to the tiles |  |  |  |  | Android Completed
199 | Adding test data |  |  | Charlotte Hutchinson Ben McGregor Rich Logan Stephen Tate |  | Completed
200 | Come up with our elevator pitch |  | #NAME? |  |  | Completed
201 | Re test all failed tests |  |  |  |  | Testing
202 | Set to portrait |  |  |  |  | Android Completed
203 | Assync Correspondence |  |  |  |  | Android Completed
204 | Profile page? |  |  |  |  | Android Completed